## Sheet1
The Grid (checklist)--UTAH: ALPINE, PROVO, AND WASATCH SCHOOLS | Assigned to | Notes
Utah contact: Whitney Wilcox--administrative advisor (385-219-6399; whitney.wilcox18@gmail.com)
Coke scholarship program takes students with "B" average for Winter Semester, 2015 to Seven-Peaks (Provo)
June 4 (Th.)--Provo, Orem, Timpview, Mountain View, Timpanogos; June 5 (Fr.)--Lehi, Wasatch, Lone Peak, AF, PG
1 yr. before (June 2014)
Contact school principals in Alpine, Provo, and Wasatch schools to see who is interested in participating | Whitney | *Get appointed contact for school
-Dave Mower (Lehi); dmower@alpinedistrict.org, 180 N 500 E, Lehi, UT 84043 (801) 768-7000
-Shawn Kelly (Wasatch); shawn.kelly@wasatch.edu, 435-654-0640 ext. 3701 930 South 500 East Heber City, UT 84032
-Karen Brown (Provo); kbrown@provo.edu, (801)-373 6550 1125 North University Ave Provo, Utah 84604
- Todd McKee (Timpview); tmckee@provo.edu, 3570 Timpview Dr, Provo, UT 84604 (801) 221-9720
-Theron Murphy (Timpanogos); tmurphy@alpinedistrict.org, 1450 N 200 E, Orem, UT 84057 (801) 610-8175
-Rhonda Bromley (Lone Peak); rbromley@alpinedistrict.org 10189 N 4800 W, Highland, UT 84003 (801) 717-4568
-Rachelle Bollingbroke (Orem); rbollingbroke@alpinedistrict.org, 175 S 400 E, Orem, UT 84097 (801) 610-8165
-Doug Finch (AF); dfinch@alpinedistrict.org, 510 Caveman Blvd, American Fork, UT 84003 (801) 756-8547
-Hank Meyer (PG); hmeyer@alpinedistrict.org, 700 E 200 S, Pleasant Grove, UT 84062 (801) 610-8170
-Taran Chun (Mountain View); tchun@alpinedistrict.org, 665 W Center St, Orem, UT 84057 (801) 610-8160
Design marketing brochures, posters, and t-shirt design | Alyssa | *3 colors print; 1 color t-shirt
Create media packets for schools (give to college advisor or other appointed contact) | Tessa
-contact list
-timeline
-t-shirt design
-scholarship brochures and other give-aways
-agreement forms
Deliver media packets and arrange to take 15 min. at kick-off school assembly | Whitney, Alyssa&Tessa | *Pick up legal/agreement forms
9 mo. Prior (Sept. 2014)
Participate in school assemblies with Coca-Cola Scholarship Program representative/drop off event poster #1 (Coca-Cola Scholarship Program; raise grades in Winter 2015); take information brochures for students + give-aways |  | 10-15 min./ drawing for prizes
--Sept. 4 (Provo @ 10:10 a.m.; Timpview @ 10:40 a.m.) | Whitney&intern
--Sept. 4 ( Mountain View @ 10:45 a.m.) | Alyssa&Tessa
--Sept. 5 (Orem @ 10:15 a.m; AF @ 11:15 a.m.) | Whitney&intern
--Sept. 5 (PG @ 11:10 a.m.) | Alyssa&Tessa
--Sept. 6 (Lone Peak @ 10:15 a.m.; Lehi @ 11:10 a.m.) | Whitney&intern
--Sept. 6 (Timpanogos @ 10:05 a.m.) | Alyssa&Tessa
--Sept. 7 (Wasatch @ 10:05 a.m.) | Alyssa&Tessa
6 mo. Prior (Dec. 2014)
Send reminder to administrators to announce to students prior to Christmas break that program starts in three weeks | Whitney
Set up 2nd assembly time and date; plan and arrange details for competition | Whitney
Bring on two more interns to help with event (Jan.-May 2015) | Whitney
5 mo. Prior (Jan. 2015)
Get final t-shirt design approved and send to printer | Whitney | *cooltshirts.com; Patty
Take around event poster #2 (the program has started) to schools | Depends
2nd assemblies; create excitement for activity and raising grades |  | *Hold competition among
--Jan. 15 (Provo @ 10:10 a.m.; Lehi @ 11:40 a.m.) | Whitney&intern | students; take give-aways
--Jan. 15 (AF @ 10:15 a.m.; PG @ 11:05 a.m.) | Tessa&intern | 15-20 min.
--Jan. 15 (Wasatch @ 11:15 a.m.) | Alyssa&intern
--Jan. 16 (Lone Peak @ 11:10 a.m.) | Whitney&intern
--Jan. 16 (Timpview @ 10:15 a.m.; Timpanogos @ 11:10 a.m.) | Tessa&intern
--Jan. 16 (Mountain View @ 10:10 a.m.; Orem @ 11:05 a.m.) | Alyssa&intern
4 mo. Prior (Feb. 2015)
Rent out Seven-Peaks (June 4 and June 5, 2015) | Alyssa | *Platinum pkg. = lunch, drink
Place order for t-shirts ("Coca-Cola Scholarship Program") | Whitney
Order H20 Dasani bottles with special packaging ("You've worked hard, now it's time to be rewarded." Coke Scholarship) | Whitney
Order "Coca-Cola" wristbands | Tessa | *Different color for schools
Provo: Green
Timpview: Orange
Lone Peak: Black
Mountain View: Maroon
AF: White
PG: Dark Bllue
Timponogos: Light Blue
Wasatch: Yellow
Orem: Gold
Lehi: Grey
Call around for best printing deals | intern
3 mo. Prior (March 2015)
Schedule school buses | Alyssa | *15 buses; 3 each school; 2 days
Design event poster and flyers | Alyssa
2 mo. Prior (April 2015)
Take 3rd event poster to schools | interns | *different according to school
Gather list of approved students from counselors | interns | included in packet
Print off flyers
Drop off flyers and permission slips to pass out to students to take home | interns
Schedule box truck | intern
1 mo. Prior (May 2015)
Get final count of students; pick up permission slips and call to confirm at Seven-Peaks | Whitney
Confirm bus count; get drivers a check-list of students | intern
Drop off student check-lists (x3 per school, one for each bus) for school administrators to use when loading buses
Pick up: water bottles, t-shirts, wrist bands, printed brochures and information | intern
Make sign-ups for students and evals | intern
Blow up big event poster and make "Coca-Cola Scholarship Program" poster | intern | *227%, color
Assemble supply box: phone list and binder, pens, sign ups and evals for students to fill out, tape, paper clips, etc. | intern
Make signs for each school (x3), print, laminate and tape on a wooden pole | intern
Order long red table cloths (x2) | intern
Right before activity
Load van: long tables (x17), red tablecloths (x2), supply box, water bottles, printed scholarship brochures, H20 bottles, t-shirt boxes, etc. | intern
First aid kit and emergency contact info./release forms | intern
Load event posters and easels | intern
After event
Feedback and evaluation from schools | All
Cleanup | All
Journal | All
Send out thank-yous | Whitney